Checklist for MT DPHHS Electronic Case Reporting (eCR) Implementation

- Register intent of eCR implementation with MT DPHHS.

- Complete eCR implementation with your EHR Vendor, CDC eCR Onboarding Team, and APHL.

  - Complete all required EHR checklist items or testing scenarios.

  - eICRs must be formatted according to the HL7 standards for electronic initial case report (eICR) for CDA or FHIR.

  - Implement triggering for all conditions (if EHR capable).

    - Download and implement the most recent condition code set from eRSD.

    - MT DPHHS encourages all current and onboarding healthcare organizations or eligible providers to implement triggering for all conditions.

  - Establish connection with APHL’s platform – AIMS.

  - Confirm successful receipt back of a Reportability Response (RR) after sending an eCR.

- Schedule Soft Go-Live date with approval from CDC Onboarding Team, APHL, and all applicable PHAs.

- Complete Soft Go-Live and address issues identified in Data Quality (DQ) Monitoring Report.

  - During the Soft Go-Live the eCR testing team will run messages through the Data Quality (DQ) Schematron and provide a DQ Monitoring Report of the findings including any identified issues that need to be addressed.

- Review DQ Monitoring Report and fix any necessary errors/problems.

  - Provide responses to identified issues back to CDC Onboarding Team.

- Schedule a Go-Live date with MT DPHHS to start sending production eICRs.

  - Coordination will require the approval of all involved PHAs.

- Enter PHA Validation Phase after approval from CDC, APHL, and MT DPHHS for production data to be sent through the production feed.

- MT DPHHS eCR team conducts data quality evaluation of production eICRs and provides any necessary changes required before moving into production.

  - Review the Data Element Priority List to see what data elements will be evaluated for completeness and accuracy within eICRs during the PHA validation phase.

  - MT DPHHS will require an extend review period while preparing our surveillance system for eCR implementation into production.

- MT DPHHS approves HCO eICRs to move into the production environment of our surveillance system, NBS.

  - HCOs MUST continue with manual reporting methods at this time.

- Received formal email notification that manual reporting methods can be stopped for certain conditions.

  - Conditions will be validated and implemented in our surveillance system on a rolling basis.

- Maintain standard of eICRs delivered to MT DPHHS.

  - HCOs are responsible for continuing to update the to the most recent Reportable Condition Trigger Codes (RCTC) from eRSD.

  - Failure to meet the data quality requirements may result in MT DPHHS requiring manual reporting methods to continue.

Acronyms

AIMS – APHL Informatics Messaging Services

APHL – Association for Public Health Laboratories

CDA – Clinical Document Architecture

CDC – Centers for Disease Control and Prevention

CSTE – Council of State and Territorial Epidemiologists

eCR – Electronic Case Reporting or Electronic Case Report

eICR – Electronic Initial Case Report

EHR – Electronic Health Record

eRSD – Electronic Reporting and Surveillance Distribution

FHIR – Fast Healthcare Interoperability Resources

HL7 – Health Level 7

MT DPHHS – Montana Department of Health and Human Services

NBS – NEDSS Base System

NEDSS – National Electronic Disease Surveillance System

PHA – Public Health Association

RR – Reportability Response